Table of Contents

Document Modification History	3

1.	Introduction	4

1.1 Project details	4

1.2 Purpose of the Consultation Strategy	4

1.3 Audience	4

2.	Background	4

2.1 Project overview	4

2.2 Importance of stakeholder engagement for project success	5

3.	Stakeholder engagement objectives and scope	6

3.1	Stakeholder engagement objectives	6

Stakeholder identification and analysis	6

4.1 Stakeholder identification and analysis	6

5.	Strategic approach	10

5.1 Engagement methods	10

5.2 Timing	11

5.3 Consultation questions	13

6.	Communications	14

6.1 Communications objectives	14

6.2 Communications methods	14

8.	Evaluation	16

Document Modification History

| Version | Status | Release date | Summary of changes |
| --- | --- | --- | --- |
| V1 | Current | 12 September 2025 | Document published |
| V1.1 | Current | 23 January 2026 | Dates Amended. Amendment to list of organisations in Section 4.1 |

- Introduction

1.1 Project details

| Project full name and code: | 26-001 CHC Career Development and Employment Services project |
| --- | --- |
| Project shortform name: | Career Development and Employment |
| Project Manager: | Jane Mancini |
| Stakeholder Engagement Manager: | Lauren Palmer |

1.2 Purpose of the Consultation Strategy

The purpose of the Consultation Strategy (strategy) is to support the review of:

- CHC41215 Certificate IV in Career Development

- CHC81315 Graduate Certificate in Career Development Practice

- CHC41115 Certificate IV in Employment Services.

The strategy includes identification and mapping of key stakeholder groups, and outlines consultation objectives, methods and timing of engagement activities. It also includes communication objectives and methods. The strategy is underpinned by the HumanAbility Stakeholder Engagement Strategy.

1.3 Audience

The audience for this strategy is the Project Sponsor, Project Director, Project Team, Technical Committee, Stakeholder Engagement Manager, Department of Employment and Workplace Relations (DEWR) and key stakeholder groups.

- Background

2.1 Project overview

The proposed review will ensure the qualifications reflect the full breadth of practitioner responsibilities and support the sector’s contribution to national workforce resilience and economic participation. The CHC Employment Services and Career Development qualifications have not undergone a full review since their release in 2015. In the context of significant shifts in labour market dynamics, service delivery models, and learner demographics, a comprehensive review is proposed. This review will ensure the qualifications remain relevant, inclusive, and aligned with national workforce development priorities and the evolving expectations of the career development sector.

Career development and employment services practitioners are essential contributors to Australia’s workforce infrastructure. They provide tailored, evidence-based support to individuals navigating complex education and employment transitions. Their services include career planning, labour market navigation, CV and interview preparation, and guidance on vocational and higher education pathways. These services are particularly critical for individuals facing structural barriers to employment, such as young people, mature-age workers, and culturally and linguistically diverse communities.

A result of this is that frontline employment consultants increasingly concentrate on providing intensive support for participants with multiple barriers to employment. Stakeholders, including providers, have identified the need for training in dealing with challenging behaviours from clients. Existing training related to soft skills in the Learning Centre is limited or outdated.

The Disability Royal Commission identified several training gaps for Disability Employment Services (DES) staff, and advocated for resources that would improve disability awareness, cultural competence, knowledge of human rights, reasonable adjustments, employer engagement, and service guidelines and procedures.

Initiatives such as the Victorian Public Service Commission’s ‘Barring Djinang: First Peoples Workforce Development Strategy’ and its Indigenous Skills and Employment Program acknowledge that career development, employment services and support for First Nations people are successful when they are culturally informed, safe and responsive. Qualifications that embed these principles will improve outcomes for career development practitioners and clients alike.

While practitioners report high confidence in interpersonal and ethical competencies, they express lower confidence in technical areas such as programme evaluation, needs assessment, and the application of career development frameworks. These competencies are essential for evidence-based practice, service quality assurance, and alignment with national standards. Stakeholders told the Committee on Workforce Australia Employment Services that in Australia—and globally—there is an increasing focus on job ready participants being managed via online or hybrid services delivered by the public sector.

2.2 Importance of stakeholder engagement for project success

Successful stakeholder engagement is critical to the project’s success and value.

This means hearing from a wide range of people: training providers, employers, industry bodies, unions, government agencies, people working in career education and employment services roles, students – as well as ensuring we reflect the specific needs of First Nations communities, culturally and linguistically diverse providers, participants and workers, and services in regional, remote and rural Australia.

It is also deeply important to us to hear from people who use career development and employment services in the work of this project.

HumanAbility is conscious of the importance of ensuring different groups can engage in ways that work best for them, within reasonable timelines for them and the project. We will endeavour to take a tailored approach when hearing from others.

- Stakeholder engagement objectives and scope

- Stakeholder engagement objectives

- Propose changes to the qualification to deliver on the technical needs of key stakeholder groups through the establishment of a technical committee.

- Through ongoing engagement, align changes to the training products in scope to the broader perspectives and objectives of key stakeholders in the career development and employment services.

- Collect thorough, detailed feedback from across the career development and employment services sectors to inform potential changes to the training products in scope.

- Support different stakeholder groups to engage with the review process through tailored outreach methods, and bespoke opportunities for consultation.

- Provide effective, timely, accessible and transparent communication with stakeholders about consultation opportunities, progress and outcomes of the project.

- Ensure stakeholders are valued, included and heard throughout the project – from its early exploratory stages to its final outcomes.

- Monitor and review the impact of the project.

The scope of stakeholder engagement is identified in Section 5. Any forms of stakeholder engagement not identified in Section 5 should be considered “out of scope”.

Stakeholder identification and analysis

4.1 Stakeholder identification and analysis

The table below outlines the key stakeholders for this project and the value their involvement brings to the project. Stakeholders have been identified in accordance with the International Association of Public Participation (IAP2) principles and practices of engagement.

The benefits of engagement inform how we will engage with each stakeholder group (outlined in Section 5). Through the project lifecycle, we will continue to identify key stakeholder organisations and individuals to consult and the appropriate methods of engagement, in consultation with the Technical Committee. Other Jobs and Skills Councils are not listed below, as the project scope is limited to reviewing units in HumanAbility’s remit.

| Stakeholders | Organisations | Benefits of involvement |
| --- | --- | --- |
| Human Services Industry Advisory Committees (IAC). | Human (Community) Services IAC Note: See HumanAbility website for list of current IAC members. | Strategic advice on project progress via expert representatives across the career development and employment services sectors. |
| Technical Committee | Note: See Terms of Reference for full Technical Committee member list. Committee is constituted of the training sector (a balance of TAFE and private and public RTO representatives), as well as workforce, service providers, unions and peak bodies. | Technical advice based on sector expertise and direct experience and understanding of the qualifications in scope. |
| Subject matter expert (SME) pool/s | SMEs from across the career development and employment services sectors that can provide targeted feedback on emerging issues of importance identified prior or during the project. Multiple panels may be established depending on the granular detail level, segmentation of units and required expertise for consultation. | Technical insight through specialist knowledge of identified issues relating to the career education and employment services qualifications and/or related occupations. |
| RTOs and educational experts | Including, but not limited to TAFEs, Universities and RTOs that deliver or intend to deliver the qualifications, trainers and assessors, curriculum maintenance managers. | Insights from direct experience delivering the qualifications in scope. |
| Industry peak bodies | Including but not limited to: Career Industry Council of Australia National Employment Services Association National Disability Services Amplify Alliance Australia | Insights on opportunities to improve uptake or value of the qualifications, training and career pathways, regulatory compliance, and emergent, related sector-wide developments. |
| Employers | Employers of career development and employment services workers from a range of sectors (including education, disability employment services, private practice) utilising or affected by the qualifications. Employers of career development and employment services that are currently not using the qualifications for their workforce. | Insights on opportunities to improve uptake or value of the qualifications, training and career pathways, regulatory compliance, and emergent, related sector-wide developments. |
| Unions with relevant coverage | Including, but not limited to: Australian Services Union Australian Education Union Independent Education Union | Ensure changes to the qualifications support improved career progression, contemporary skills and knowledge needs, safety, recognition, workforce support, attraction and retention. |
| Relevant federal, state and territory government departments and agencies | Including, but not limited to: Department of Employment and Workplace Relations (Commonwealth) Department of Health, Disability and Ageing (Commonwealth) Department of Social Services National Indigenous Australians Agency (NIAA) National Disability Insurance Agency (NDIA) NSW Department of Education Department of Education (Victoria) Department of Education (QLD) Department of Education (WA) Department for Education (SA) Department for Education, Children and Young People (TAS) ACT Education Directorate Department of Education (NT) State Training Authorities, Relevant providers or Government stewards of career development and employment services. | Input on the project as funders of training placements, incentives and initiatives and as market stewards. |
| Industry Training Advisory Boards / Councils (ITABs) | Community Services and Health ITAB (NSW) Community Skills WA QCOSS (QLD) Industry Skills Advisory Council NT South Australian Skills Commission Victorian Skills Authority | Direct experience and understanding of the qualifications and related occupations, strong state-based connections with industry and training providers. |
| Priority cohort - Aboriginal and Torres Strait Islander people | Including, but not limited to: Aboriginal and Torres Strait Islander Community Controlled Organisations (ACCO’s) National Indigenous Employment and Training Alliance (NIETA) First Nations people working in the Career Development and Employment Services Sector | Ensures the training product meets the specific needs of First Nations employers, workers and service users. |
| Priority cohort – people with disability | Including, but not limited to: Swinburne University of Technology Disability Employment Centre of Excellence Disability Employment Australia Inclusion Australia Disability Peoples Organisations (DPOs) Disability Advocacy Network Australia (DANA) Australian Federation of Disability Organisations (AFDO) People with a disability working in the Career Development and Employment Services Sector | Ensures the training product meets the specific needs of people with disability employers, workers and service users. |

- Strategic approach

5.1 Engagement methods

| Method | Purpose | Who | Timing |
| --- | --- | --- | --- |
| Industry Advisory Committee consultation | Provide strategic advice to HumanAbility via expert representatives across the career development and employment sectors on project progress. | As listed in section 4.1 | As requested in IAC meetings |
| Technical Committee consultation | Support development work and provide technical advice and feedback on the consultation strategy. The Committee will include representatives from key stakeholder groups and national coverage. |  | Throughout the project |
| 16 virtual Functional analysis interviews and 2 functional workshops | Discuss settings, current roles, functions and tasks, identify jurisdictional and other relevant nuances, and identify opportunities for improving skills gaps, workforce attraction, retention and career pathways. Participants will be drawn from all states and territories from metropolitan, regional, and remote areas. | Employers, unions and identified SMEs |  |
| Government and Public consultation workshops (12 face to face, 3 virtual) | Group discussions to understand needs, challenges, gaps, solutions and improvements for the qualifications. This includes: - 3 virtual workshops - And 12 face to face workshops held in each state and territory focusing on different qualifications in scope. Further workshops will take place as required in a second phase of consultation. | All groups affected/ involved in training or service delivery. Technical experience, understanding of the qualifications preferred |  |
| Engagement with subject matter expert (SME) pools | Consultation with identified subject matter experts to understand specific needs and improvements for the qualifications. This may include reference groups for participants in career development and employment services. | SMEs with specialist knowledge to inform project findings. | As required |
| Sector- facilitated workshops | Receive feedback through workshops hosted by sector organisations or association gatherings. | All stakeholders |  |
| Surveys, online feedback and submissions | Stakeholders can provide a response to a survey, freeform feedback or full policy submissions in response to the project, to add value to feedback already provided in workshops, or in place of it. |  |  |
| Leveraging existing meetings with critical partners | Establishing or utilising periodic meetings with Disability Employment Centre of Excellence, Departments and industry stakeholders to strengthen project participation and ensure alignment to government reforms and objectives. |  |  |
| 3 virtual professional development workshops | Focus on the new qualifications and how good practice for delivery and assessment will be conducted. Workshop recordings will be available on the HumanAbility website. | Trainers and assessors |  |

5.2 Timing

| Project Stage | Key Deliverables |
| --- | --- |
| Stage 1 Project set up Scheduled Start Date: 1 August 2025 Schedule End Date: 26 September 2025 | Establish project team Draft a project plan and consultation strategy Establish Technical Committee (TC) and seek feedback on draft consultation strategy (Meeting 1) Submit project plan and consultation strategy to DEWR Create a project page on website, publishing the stakeholder engagement plan and timelines Publish on website stakeholder engagement plan |
| Stage 2 Initial development Scheduled Start Date: 29 September 2025 Schedule End Date: 6 March 2026 | Early check-ins with priority stakeholders regarding the intent and stages of the project Functional analysis consultation, including but not limited to 16 x interviews 2 x virtual functional analysis workshops held – One Career development and One Employment Services Functional analysis report finalised, and consultation paper developed Develop draft qualification and units of competency Hold Technical Committee meeting seeking feedback on consultation paper and draft qualification and units of competency (Meeting 2) |
| Stage 3 Public and government consultation Scheduled Start Date: 9 March 2026 Scheduled End Date: 25 May 2026 | Draft qualification and units of competency published on HumanAbility’s website with opportunities to submit feedback. Send communique to all key public and government stakeholders including RTOs and TAFEs currently delivering the nationally accredited qualification that consultation is open and details on how feedback can be submitted Conduct workshops 12 face to face workshops (8 urban and 4 regional) 3 virtual workshops, other methods as required. Consultation log made released on HumanAbility’s website with the log regularly updated with feedback. |
| Stage 4 Incorporating feedback from public and government consultation period Scheduled Start Date: 25 May 2026 Scheduled End Date: 3 July 2026 | Review all feedback received, and update the consultation register and actions taken including justification where required Meet with TC to inform decisions around conflicting stakeholder feedback (Meeting 3) Summary of consultation feedback and actions taken published on HumanAbility’s website Draft qualification and units of competency finalised and published on HumanAbility’s website with opportunity to comment |
| Stage 5 Senior Official’s Check Scheduled Start Date: 6 July 2026 Schedule End Date: 31 July 2026 | Consultation held with Commonwealth and state/territory Senior Responsible Officers Feedback incorporated into final documentation |
| Stage 6 Finalisation and Submission to Assurance Body Scheduled Start Date: 3 August 2026 Schedule End Date: 21 August 2026 | Internal QA of materials conducted Qualification and units of competency uploaded onto the VET National Training Register – in draft format Companion volume updated to reflect changes to the training package and including mapping information Draft submission finalised and submitted to the Assurance Body for consideration |
| Stage 7 Assurance Body and Skills Ministers’ Endorsement Scheduled Start Date: 24 August 2026 Schedule End Date: 2 October 2026 | Provision of any additional information the Assurance Body may require. Submission presented to Skills Ministers for endorsement |
| Stage 8 Release and post endorsement Schedule Start Date: 12 October 2026 Scheduled End Date: 19 November 2026 | Endorsed training products and associated companion volume released on the VET National Training Register Website updated with final outcomes of the project Communique sent to all RTOs delivering the qualification and ASQA advising of the entry requirement changes 3 virtual professional development workshops held on the new qualification |

5.3 Consultation questions

Consultation questions will be developed by the project team and refined by the Technical Committee. Consultation with stakeholders will be structured to:

- Understand changes to the sector and the skills, knowledge, practice and requirements needed for the training products under revision, as well as the current workforce, skills gaps, challenges, shortages, opportunities and potential solutions.

- Identify functions that are common across all settings/specific settings and pathways within the sector, and inform changes for the qualifications, units of competency and skill sets.

- Provide advice on the development of resources, guidance on delivery and pathways information.

- Communications

6.1 Communications objectives

- Raise awareness of the project and its objectives among career development and employment services sector stakeholders.

- Promote genuine, inclusive consultation opportunities, key dates, project progress and outcomes to stakeholders through a variety of communications channels.

- Foster the involvement of a diverse range of stakeholders to gather rich, diverse and valuable industry insights, experience and expertise to inform the project.

- Build stakeholder trust and credibility through effective, timely, and transparent communication.

- Ensure an accessible and inclusive communications approach in line with the Australian Government Style Guide (https://www.stylemanual.gov.au/accessible-and-inclusive-content).

6.2 Communications methods

| Communications channel / tool | Purpose / Details |
| --- | --- |
| Fact sheet | Provide an overview of the project and how to participate. Includes link to website/project page. |
| HumanAbility website | Provide a dedicated webpage where all project information and activities can be accessed easily, outline key details of the project, timelines, activities in preparation for consultation and communication across all channels. Links for stakeholders to register interest, provide submissions and feedback, register for consultation sessions and access project updates. |
| Emails | Provide information to stakeholders around participation opportunities and project’s progress. |
| HumanAbility newsletter articles | Provide project updates in HumanAbility’s monthly newsletter. |
| Social media | Publish project consultation opportunities, updates, and other activities on HumanAbility’s LinkedIn and Facebook accounts to alert followers, increase Humanability’s social media reach through stakeholders sharing content. Direct people to the project webpage and encourage project engagement. |
| Industry news media | Leverage relationships with key stakeholder organisations and ask them to share our project consultation opportunities and other activities. |
| Connect and communicate with networks | Contact and link in with industry networks, peak bodies, existing workforce committees/groups and IAC networks to promote consultations. Identify and connect with communications departments of industry stakeholders to encourage promotion of consultation activities Email key messages about the project, image/s, information sheet Tag organisations in social media where relevant – link to website consultation page. Link in with industry events/meetings and hand out material (e.g. info sheet) |
| Regular updates and meetings with STAs /ITABs/CMM | Provide status reports and updates via emails and regular meetings. These activities will occur throughout the project to ensure STAs/ITABs/CMM are kept informed and abreast of any issues or concerns raised during the project. |
| Events/speaking engagements | Attend external events/speaking engagements or host HumanAbility events, online or in person – providing updates to stakeholders |
| Resources | Publish resources - the companion volume will be updated to reflect the new qualifications, skill sets and units of competency, along with guidance on delivery, pathways and mapping information. |

- Feedback and Consultation Log

Stakeholder feedback will be gathered primarily through consultations, workshops and engagements, as well as surveys, and then quantified, analysed qualitatively (thematic analysis), with outcomes/response tracked as required by the Training Package Organising Framework.

Stakeholders may also submit feedback via the Training Product Advice Service (web form) and the project email address trainingproducts@humanability.com.au, which appears on the project page.

The consultation log will capture individual feedback, the organisation name, stakeholder type and the method of communication/consultation. Stakeholder names and contact details will also be collected to enable HumanAbility to clarify and follow up on the feedback if needed. However, these are not included in the published version of the log and are not submitted to the funding body.

As the feedback is reviewed, the action taken in response to the feedback will be documented in the consultation log. Where feedback is not incorporated, the rationale for this will also be documented.

Where feasible, the themes identified from consultation workshops will be added to the consultation log. The consultation log will be published on the project page after consultations and incorporation of feedback is complete.

- Evaluation

The effectiveness of the Consultation Strategy will be evaluated using the following measures:

- analysis of stakeholder type and locations

- number of interviews achieved in pre-draft and functional analysis work

- attendance at consultation workshops

- number of dedicated website page visits and submissions made in the portal

- social media posts, engagement and reach (on HumanAbility social media pages and other social media pages)

- newsletter articles / news items published by stakeholders

- meetings held / attendance / topics

- an increase in enrolments and completions of the relevant qualifications.

The Technical Committee and Industry Advisory Committee will also be asked to provide advice relating to the effectiveness of the Consultation Strategy in driving project outcomes.