Optical Dispensing Qualification Review Project

Consultation Strategy

September 2024

Table of Contents

1.	Introduction	3

1.1 Project details	3

1.2 Purpose of the Consultation Strategy	3

1.3 Audience	3

2.	Background	3

2.1 Project overview	3

2.2 Importance of stakeholder engagement for project success	4

3.	Stakeholder engagement objectives and scope	4

3.1 Stakeholder engagement objectives	4

3.2 Scope of stakeholder engagement activities	4

4.	Stakeholder identification and analysis	5

4.1 Stakeholder identification	5

4.2 Stakeholder categories and analysis	5

5.	Strategic approach	7

5.1 Engagement methods	7

5.2 Timing	10

5.3 Consultation questions	11

6.	Communications	11

6.1 Communications objectives	11

6.2 Communications methods	12

7.	Feedback and Consultation Log	13

8.	Evaluation of Consultation Strategy	13

# Introduction

## 1.1 Project details

| Project full name and code: | 24-005 HLT Optical Dispensing: Qualification Review |
| --- | --- |
| Project shortform name: | Optical Dispensing |
| Project Manager: | Evan Cooper |
| Consultation Manager: | Lisa Lawton |

## 1.2 Purpose of the Consultation Strategy

The purpose of the Consultation Strategy is to support the review HLT47815 Certificate IV in Optical Dispensing. The strategy includes identification and mapping of key stakeholder groups, and outlines consultation objectives, methods and timing of consultation activities. It also includes communication objectives, methods and an action plan for each stage of the project.

The strategy is underpinned by the HumanAbility Stakeholder Engagement Plan and Engagement Principles.

## 1.3 Audience

The audience for this strategy is the Project Manager, Technical Committee, Consultation Manager, Project Team, Department of Employment and Workplace Relations (DEWR) and key stakeholder groups.

# Background

## 2.1 Project overview

The aim of this project is to review and update the HLT47815 Certificate IV in Optical Dispensing qualification to ensure it is aligned with current industry needs, skills, practice, technologies, and safety and wellbeing outcomes for clients.

The qualification was last reviewed in 2015 and is now out of date. The core units and electives included in Certificate IV do not fully align with the needs of the industry or the diverse roles that optical dispensers are expected to perform.

Enhancing the qualification is essential to ensure that future optical dispensers possess the knowledge and skills needed to thrive in a dynamic marketplace and meet future needs.

Since the last review, the sector has experienced significant expansion and transformation driven by technological advancements across the industry from production to prescription, as well as changes in consumer expectations and increased demand for specialised eyecare services. The increasing complexity of client needs highlight the need for enhanced digital capabilities within the training. Practitioners must not only retain traditional skills but also acquire new competencies in digital measurement tools, online service delivery, and telehealth.

Skills and technology enhancements are also needed to address emerging health challenges like myopia, now recognised as a global epidemic particularly affecting children.

Enhancing the qualification will equip optical dispensers with the skills needed to meet significant growth and change in this industry. The review will also clarify the pathways for career progression, ensure the core units and electives are fit-for-purpose, and explore the feasibility of creating targeted skill sets. There is an opportunity to improve quality, standards, and consistency across the sector

## 2.2 Importance of stakeholder engagement for project success

Successful stakeholder engagement is critical to the project. It is important to hear from a diverse range of voices including training providers, employers, industry bodies, government agencies, people working in Optical Dispensing roles across different settings and students.

HumanAbility will engage with key stakeholders through a range of consultation activities to gather insights and feedback that will play a key role in shaping the project and informing changes to the Optical Dispensing qualification.

# Stakeholder engagement objectives and scope

## 3.1 Stakeholder engagement objectives

- Establish and coordinate a Technical Committee with representatives from key stakeholder groups including training providers, optical sector employers, industry bodies, and government agencies.

- Foster collaboration and dialogue among stakeholders from diverse sectors including training providers, optical sector employers and workers, unions, industry bodies, government agencies, students, and direct beneficiaries of optical services and products.

- Gather diverse perspectives and insights to inform changes to the optical dispensing qualification.

- Provide effective, timely and transparent communication with stakeholders about consultation opportunities, progress, and outcomes of the project.

- Ensure stakeholders feel valued, included and heard throughout the project.

- Monitor and review the impact of the project.

## 3.2 Scope of stakeholder engagement activities

In Scope

- Consultation with key stakeholders across the optical sector to review and update the qualification HLT47815 Certificate IV in Optical Dispensing to reflect current and future skills, knowledge, and practice requirements.

- Consultation to review units of competency and explore the feasibility of creating targeted skill sets to meet industry needs.

- Engagement methods and schedule of activities as outlined in Section 5.

Out of Scope

- Engagement methods and activities outside of the project lifecycle and/or not listed under Section 5.

# Stakeholder identification and analysis

## 4.1 Stakeholder identification

Stakeholder groups have been identified and mapped in accordance with the International Association of Public Participation (IAP2) principles and practices of engagement.

The table below outlines the key stakeholder, the benefits of their involvement, the level of interest/influence or expertise they hold, and level of participation they have in the decision-making process.

The mapping exercise identifies how we will engage with each stakeholder group and what methods will be applied - as outlined in Section 5.

Further stakeholder analysis, in consultation with the Technical Committee, will identify key stakeholder organisations and individuals to consult throughout the project lifecycle, including the methods of engagement.

A stakeholder register will be developed to capture intended and actual consultation outcomes.

## 4.2 Stakeholder categories and analysis

| Stakeholder group | Organisation | Benefits of involvement |
| --- | --- | --- |
| Consultation with Health Industry Advisory Committee |  | Direct experience and understanding of the Optical Dispensing qualification Provide advice to HumanAbility via expert representatives across the sector |
| Technical Committee with expert representatives from across the sector | Note: See Terms of Reference on the website for full Technical Committee list The Technical Committee for this project is predominantly made up of national body representatives. This qualification is only delivered by two NSW based RTOs on behalf of all states/territories. National body representatives were selected to ensure all states and territories were represented. | Direct experience and understanding of the optical dispensing qualification and related occupations Provide advice to HumanAbility as expert representatives from across the sector |
| RTOs and educational experts. | Including, but not limited to: - Australasian College of Optical Dispensing (ACOD) (NSW) - TAFE NSW (NSW) - A selection of TAFEs and RTOs nationally | Direct experience and understanding of the qualification / needs of the industry Note: Australasian College of Optical Dispensing and TAFE NSW have the qualification on scope. Consultation will include a broader collection of training providers to understand delivery barriers and why it is not included on scope |
| Assurance and regulatory bodies / Industry peak | - Product Safety Australia | Have influence on the optical systems, practice and products Advocate for improved training and pathway opportunities for optical workforce Improve quality, standards, and consistency across the sector |
| Employers across the optical dispensing sector: | Employers including, but not limited to: - Eyecare Plus - George and Matilda - Optical Superstore - Specsavers - ProVision - Bailey Nelson - Oscar Wylee - CR Surfacing - EssilorLuxottica - Rodenstock Australia - HOYA - Carl Zeiss - Bupa Optical - Teachers Health Fund - The Optical Company - 1001 Optometry | Direct experience in attracting, recruiting, and retaining the workforce |
| Subject matter experts (SME) | SMEs from across the optical dispensing sector | Extensive knowledge and experience across the optical dispensing sector |
| Jobs and Skills Councils (JSC) | - Future Skills Organisation - SACSA | For an activity that will impact other JSCs, consultation with impacted JSCs is required |
| Industry Training Advisory Boards |  | Understanding of the qualification |
| Unions | Health Services Union | Advocate for improved training and pathway opportunities for optical roles |
| Government agencies -state |  | Develop state-based optical strategies, have high impact through funding models and place-based initiatives |
| Government agencies - national |  | Develop national optical sector strategies |
| Priority cohort - Aboriginal and Torres Strait Islanders | - National Aboriginal Community Controlled Health Organisation (NACCHO) | Provides First Nations people with the opportunity to actively contribute to project outcomes. Direct beneficiaries of improvements to the sector. Consultation can be designed in partnership with National Aboriginal Community Controlled Health Organisation (NACCHO). |
| Not-for-profit organisations | - Fred Hollows Foundation - Vision Australia - Lions Eye Institute | Providing services to the sector |
| Senior Officials | Commonwealth and state/territory Senior Responsible Officers | Ensuring issues raised throughout consultation are addressed appropriately. |

# Strategic approach

## 5.1 Engagement methods

| Method | Purpose | Who | Frequency |
| --- | --- | --- | --- |
| Consultation with Health Industry Advisory Committee (IAC) | To provide advice on the establishment of Technical Committee, suggestions for engagement and feedback on project deliverables | Key influencers | At scheduled IAC meetings (during the lifecycle of the project) |
| Consultation with Technical Committee | To support development, and provide advice The Committee will include representatives from key stakeholder groups and national coverage. The Committee will provide input and feedback on the project consultation strategy. | As listed in section 4.2 | As needed throughout the project lifecycle |
| 1:1 interviews | 16 interviews in each state/territory, metro, regional and remote settings This will include interviews with employers to discuss settings, current roles, functions, and tasks for the industry ensuring that nuances between different jurisdictions and regulatory requirements are identified A selection of RTOs/TAFEs that do not currently have the qualification on scope to understand why it is not included. | Selection of employers and SMEs as listed in section 4.2 | September – October 2024 |
| Functional Analysis workshop online | One virtual functional analysis workshop will be undertaken with participants being drawn from across all states and including metropolitan, regional and remote settings. | Employers and SMEs as listed in section 4.2 | September 2024 – October 2024 Note: see the website for details |
| Consultation workshops – in person | To facilitate group discussions to understand challenges and workshop possible solutions 12 face-to-face workshops (up to two workshops in each state/territory, metro and regional) | All stakeholders | November – December 2024 Proposed workshop locations/dates Perth - 4/11/24 Adelaide - 6/11/24 Alice Springs - 8/11/24* Darwin - 11/11/24 Cairns - 13/11/24* Brisbane - 14/11/24 Newcastle – 25/11/24* Sydney - 26/11/24 Albury – 28/11/24* Melbourne - 2/12/24 Canberra - 4/12/24 Hobart - 10/12/24 * Denotes a combined workshop with Audiometry and Pathology Collection Projects Note: dates and times subject to change – see website for full details |
| Consultation workshops – online | To facilitate group discussions that will help to understand needs, challenges, gaps, solutions and improvements for the qualifications 3 virtual workshops will be offered for all stakeholders | All stakeholders | November – December 2024 Proposed online workshop dates 19/11/24 13/12/24 17/12/24 Note: dates subject to change – see website for full details |
| Online portal (consultation tool) on the HumanAbility website | To engage all participants. This is a two-way channel that enables project documents, including a consultation paper to be publicly available and capture stakeholder feedback, comments, and submissions | All stakeholders | Open throughout consultation period |
| External meetings and events | To leverage opportunities to promote the project, gain buy-in and encourage participation | All stakeholders | As required |
| Cross Jobs and Skills Council (JSC) Consultation | To undertake information session/s with JSCs that have carriage of programs that intersect with this qualification review. The relevant Jobs and Skills Councils will be kept informed of the progress of review and provided with opportunities to provide feedback. | Future Skills Organisation | Throughout consultation period |
| Professional development workshops | 3 virtual workshops To conduct professional development workshops on the new training package components and good practice for delivery and assessment A recording of the virtual professional development workshops will be made available on the HumanAbility website. | Trainers and assessors | July 2025 |
| Senior Official’s Check | To ensure any issues raised through consultation have been addressed appropriately. | Commonwealth and state/territory Senior Responsible Officers | 6 Jan 2025 – 31 Jan 2025 |

## 5.2 Timing

| Project stage | Timing | Engagement methods |
| --- | --- | --- |
| Project set up and initial drafting | July – August 2024 | - Consultation with Health IAC – to gather insights on Technical Committee membership and stakeholder identification - Consultation with Technical Committee to gather advice on Consultation Strategy and initial draft products/deliverables - Written communications/publications |
| Public and government consultation and incorporating feedback | September - March 2025 | - All methods as above - Technical Committee to gather advice on incorporating feedback - Include information in the consultation log about whether feedback was incorporated or if not, that the stakeholder was responded to - Written communications/publications |
| Final submissions and reporting | June 2025 | - Technical Committee to gather advice on final draft products/deliverables - Consultation with IAC - Written communications/publications - Submissions / letters |
| Senior Official’s Check | 6 Jan 2025 – 31 Jan 2025 | - Draft materials and completed consultation log provided to Commonwealth and state/territory Senior Responsible Officers for review - Feedback incorporated into final documentation |
| Endorsement and release | June – July 2025 | - Written communications/publications - Professional development workshops |

## 5.3 Consultation questions

Consultation questions will be developed by the project team and refined by the Technical Committee.

Consultation with stakeholders will be structured to:

- Understand the current optical dispensing industry changes and the skills, knowledge, practice and requirements needed for the HLT47815 Certificate IV in Optical Dispensing qualification.

- Understand the current challenges, gaps, opportunities, and potential solutions.

- Identify and inform changes for the qualification, units of competency and skill sets.

- Identify functions that are common across all settings/specific settings and pathways within the sector.

- Provide advice on the development of resources, guidance on delivery and pathways information.

- Understand why RTOs/TAFEs do not have the current qualification on scope and what prevents them from delivery of the future qualification on their jurisdiction.

# Communications

## 6.1 Communications objectives

- Raise awareness of the project and its objectives among optical industry stakeholders.

- Promote consultation opportunities, key dates, project progress and outcomes to stakeholders through a variety of communications channels.

- Foster the involvement of a diverse range of stakeholders to gather rich and valuable industry insights, experience, and expertise to inform the project.

- Build trust and credibility with stakeholders through effective, timely, transparent, and accessible communications.

## 6.2 Communications methods

| Communications channel / tool | Purpose / Details |
| --- | --- |
| Internal communication (meetings/email) | To keep internal stakeholders informed of project updates |
| Frequently asked questions | To outline the potential questions and answers that might come up during consultation (preparation) |
| HumanAbility website | To provide a dedicated webpage where all project information and activities can be accessed easily. This webpage will include an engagement portal for stakeholders to register interest, provide submissions and feedback, and access project updates. |
| Email/email template or campaign/mail merge | To send emails/email template letters, information and updates to stakeholders to participate in consultation / share consultation opportunities. |
| News alerts | To provide project participants and other key stakeholders with branded news alerts via email when there is a project update. |
| HumanAbility newsletter articles | To provide project updates in HumanAbility’s general newsletter. |
| Social media | To publish project consultation opportunities, updates, and other activities on HumanAbility’s social media channels including LinkedIn, Facebook, and X (Twitter) to reach as many and diverse stakeholders as possible. Social media posts will link to the HumanAbility webpage to encourage engagement on the project. Stakeholders can increase HumanAbility’s social media reach by sharing content on their social media channels. |
| Industry news media | To leverage relationships with key stakeholder organisations with newsletters to share HumanAbility project consultation opportunities and other activities. |
| Connect and communicate with networks | To contact and link in with industry networks, peak bodies, existing workforce committees/groups and IAC networks to promote the opportunity to participate in the project consultation. Identify and connect with communications departments of industry stakeholders to encourage promotion of consultation activities - Email key messages about the project, image/s, information sheet - Tag organisations in social media where relevant – link to website consultation page - Link in with industry events/meetings and hand out material (e.g. info sheet) |
| Events/speaking engagements | To host regular HumanAbility events/speaking engagements e.g. via webinar or in person – providing updates to industry and project stakeholders |
| Resources | To publish resources - the companion volume will be updated to reflect the new qualifications, skill sets and units of competency, along with guidance on delivery, pathways and mapping information. |

# Feedback and Consultation Log

Stakeholder feedback will be gathered during the consultation via workshops and interviews/surveys. Stakeholders may also submit feedback via the Training Product Advice Service (web form) and the training product project email address trainingproducts@humanability.com.au, which appears on the project page.

Surveys will be the primary mechanism for structured, individual feedback during public consultation. This ensures that feedback can be quantified, analysed qualitatively (thematic analysis) and that the outcomes/response can be tracked as required by the Training Package Organising Framework.

Individual feedback will be captured in the Consultation Log. This also captures the organisation name, stakeholder type, State and the method of communication/consultation. Stakeholder names and contact details will also be collected to enable HumanAbility to clarify and follow up on the feedback if needed. However, these are not included in the published version of the Consultation Log and are not submitted to the funding body.

As the feedback is reviewed, the action taken in response to the feedback will be documented in the Consultation Log. Where feedback is not incorporated, the rationale for this will also be documented.

Where feasible, the themes identified from consultation workshops will be added to the Consultation Log.

The Consultation log will be published to the project page after consultations and incorporation of feedback is complete.

# Evaluation of Consultation Strategy

The effectiveness of the Consultation Strategy will be evaluated using the following measures:

- Analysis of stakeholder type and location

- Number of interviews achieved in pre-draft and functional analysis work

- Attendance at consultation workshops

- Number of dedicated website page visits and submissions made in the portal

- Social media posts, engagement and reach (on HumanAbility social media pages and other social media pages)

- Newsletter articles / news items published by stakeholders

- Meetings held / attendance / topics

- An increase in enrolments and completions of the relevant qualifications.

The Technical Committee and Industry Advisory Committee will also be asked to provide advice relating to the effectiveness of the Consultation Strategy in driving project outcomes.